## Slide 1
MULTI-modal imaging of FOREnsic SciEnce Evidence - tools for Forensic Science’
COST Action CA16101
(Mar 2nd 2017- March 1st 2021)
https://multiforesee.com/
II MC meeting 06/11/2017 – Chaired by Dr S. Francese, Sheffield Hallam University, UK
Notes: Ask someone that takes minutes and highlights MC decisions proposals

## Slide 2
28 countries in total. Are 19 countries present?

## Slide 4
Development of Objective achievements.
How do we do the internal monitoring? Visual descriptive tools and reporting at the annual MC.
Designate a person, a scientific officer, to collect info and provide a monthly report to CORE group is approved by the MC. No candidates come forward at the meeting.
Proposed to ask Simona to take on the job ad-interim until she finds a replacement.
This issue is parked until the next meeting.
Responsibilities are to gather information on progress of the Action by contacting elected individuals (WG Leaders, STSM Manager, Dissemination, progress towards objectives, training schools and publication quality).
Matters arising from Last Minutes (1)
Self-nominations?

## Slide 5
MULTi-modal imaging of FOREnsic SciEnce Evidence (MULTI-FORESEE)- tools for Forensic Science - ELECTION OF WG1 LEADER
Nominations so far: Prof. Martina Marchetti-Deschmann (Austria)
MULTi-modal imaging of FOREnsic SciEnce Evidence (MULTI-FORESEE)- tools for Forensic Science - ELECTION OF THE DISSEMINATION OFFICER
Nominations so far: Prof. Ivana Ognjnanovic (Montenegro)
Matters arising from Last Minutes (2)

## Slide 6
Matters arising from Last Minutes (3)
Budget increment (EUR 14 000) due to a new networking tool (grant conferences) –
TOTAL BUDGET EUR 129,977.51

## Slide 8
COST Action CA16101 (Mar 2017- April 2021)
At the time of the I MC Meeting (02/03/2017), Participating countries
22 COST Countries, 1 Cooperating Country (Israel) – 1 European Body, ENFSI (49 participants)
To date (06/11/2017)
27 COST Countries signed the MoU- 1 Cooperating Country (Israel) – 1 European Body, ENFSI -1 IPC (Australia) – 1 NNC (Belarus) (91 MC members (full+substitutes))
NNC
NNC
IPC
IPC
NNC

## Slide 10
Financial Report is being prepared and will be submitted by the designated deadline. However….
1. Dissemination budget: EUR 4000 - spent
2. I WG1 and WG2 meetings (Porto (PT) June 2017): Available: EUR 21,660 – spent 20,367.98 - UNDERSPENT EUR 1292.02
3. STSM: Available: EUR 28,800 – spent 2500, + 9900 forecast for additional 4 – need to award another 7 by the end of January-February (EUR 16400)
4. Training School (Wakefield (UK) August 2017: Available: EUR 14,740 – spent EUR 13,016.82 – UNDERSPENT EUR 1723.18
5. Meetings (including Conference, 1 Workshop, 1 MC meeting, 1 WG1 and WG2 meetings) 6-9 Nov Krakow (PO) Available: EUR 36,450 – spent ?
6. Conference Grants- Available: EUR 8977.28 – spent EUR 0 – UNDERSPENT EUR 8977.28 (≈4 Conference grants)

## Slide 12
Network of proposers | Upon publication of the MoU and active recruitment | To date (6/11/2017)
22.5% | 35.3%* | *31.8%
Gender balance
* out of 68 full and subst. MC members
Very difficult to keep track if they are not MC full/substitute members.
Core group members: 3/6 are women
The Action Chair is a woman
At least 1/5 STSM has been awarded to woman but only 1 woman has applied
6/8 Trainees at the 2017 Training School were women. 2 out of 4 trainers were women

## Slide 13
ECI
Very difficult to keep track if they are not MC full/substitute members. Even if they are, not everybody has provided information as to whether they belong to ECI according to COST definitions.
According to the info provided 15% of the MC comprises ECI.
Roles for ECI have been proposed to side Core group members. Not yet implemented to my knowledge
At least 3/5 STSM have been awarded to ECI
7/8 Trainees at the 2017 Training School were ECI
Shotgun presentations were offered at the conference to involve as many ECI as possible –the offer was not taken
Would be helpful if conference grants could also be awarded to participate to COST conferences

## Slide 15
Network of proposers | Upon publication of the MoU and active recruitment | To date (6/11/2017)
35.7% | 46% | *48
ITC inclusiveness
ITC involvements in roles and COST activities
Training School – PARTICIPATION OF 4 MEMBERS FROM ITC/8 PARTICIPANTS (1 was eventually hospitalised and did not take part)
Conference (co-localised with workshops and WG meetings) – HOSTED BY POLAND
WG1 and WG2 Meetings – HOSTED by PORTUGAL
CORE GROUP ROLES – DISSEMINATION OFFICER – HUNGARY THEN (MONTENEGRO?)
MC Members (by country) – 48%
* Three more ITC countries. We are missing Bosnia-Herzegovina, Bulgaria, Cyprus, Luxembourg, Turkey.

## Slide 18
MoU OBJECTIVES

## Slide 19
GP1 GOALS

## Slide 20
WG TASKS
Progress report upon ending of this conference
Work at the finalisation of a document summarising knowledge gained from the two RRS undertaken
Deadline?
Structure and organisation: who how and when

## Slide 21
Production of guidelines e-document identifying strategies enabling compatibility with imaging technologies. The End Users will be TASKED with leading an interactive dialogue informing participants on needs, desirables, relevant legal and ethical issues, national requirements and guidelines for evidence recovery and preservation, protection of human rights and for admissibility in Court. – After the Workshop and the overall conference this document will start to be drafted. Core group members will be involved in the drafting but other contributions are welcome and especially from the end users. The document integrates the paper based RRS initiated by WG1
DELIVERABLE 1 – MONTH 18

## Slide 22
Notes: I did not get if this was for YEAR 1 or for YEAR 2. I am not ready to discuss the budget planning for Year 2.
For this year, as shown by a quick view of the budget expenditure, we might have to be flexible and divert unspent resources to where more needed, e.g. additional STSM, possibly a Core group meeting and there might be the chance of possibly a WG meeting where needed to consolidate the results of the RRS. In the first MC meeting the MC gave mandate to the core group to spend a maximum of EUR 5000.

## Slide 23
Notes: Again I am not sure here whether this referred to the GP 1 or the future GP2.
All the activities have been exhausted for this year (apart from STSM and conference grants) unless core group or an additional WG meeting is planned.

## Slide 24
Locations (and rough dates for future activities)
WG1 and WG2 meetings:
Workshop on facial recognition (digital strand): COST-EU IAI partnership, Amsterdam
Workshop (analytical strand):
Conference:
Training School:
WORKSHOP co-organised within IDENTITY – June 2018
1) Networking Tool Description
The 6th International Workshop on Biometrics and Forensics will cover a wide range of biometric technologies and their application to forensic science. The workshop program will last two days and it will include a series of oral and poster presentations, reviewed from members of the program committee and selected from the program chairs. Two invited talks, covering some challenging issues and outstanding results in the area of forensic biometrics will be also included. 2) Networking Tool Output
The workshop is co-organized by the action MC members and will enable to present the latest scientific results of the action activities particularly to scientist from the eastern European countries. This activity will provide a forum for scientific exchange with the related IDENTITY H2020 EU project. The workshop will provide an excellent forum for presenting and discussing the latest scientific results reached by the research teams of the COST action and to define the objectives still to be addressed as well as promising future directions. In order to disseminate the results of this scientific goal, a proceedings volume will be published including the state-of-the-art of automatic biometric recognition algorithms for the quantitative estimation of biometric evidence in forensic scenarios. 3) Justification: The International Workshop on Biometrics and Forensics is the premier scientific meeting specifically devoted to present the state of the art in the integration of biometric technologies for forensic science. This workshop series was successfully started within the scope of COST Action 2101 and then followed by COST Action IC1106. Last year the 5th edition of this workshop was organized within the framework of the EU H2020 project IDENTITY, which is still co-organizing the event as part of its networking activities. For this reasons, the workshop very well fits within the objectives of this COST action and it will enable to promote cross-fertilization among the action members and with the members of the IDENTITY consortium.

## Slide 26
Outreach activities
Dr S. Francese participated to the 4th EU Conference for Science Journalists in Copenhagen, 27/06/2017.
Dr S. Francese, and Prof. Janis Spigulis will participate to the first conference in Translational Forensics (20-23 Nov 2017) organised by Prof. J. Capelo also member of this Action
Dr S. Francese – plenary lecture at Australian and New Zealand Forensic Science Society Conference, Perth, Sept 2018
Publications
Are there any collaborations taking place within the consortium that could lead to publications?
We intend to write a document to upload on the Action’s website summarising the results of the RRSs – should the material be of publishable quality, peer review publications will be pursued.
Dr S. Francese will be editing a book for Springer in which, at large, the members of this Action are involved. The book is entitled Emerging Technologies for the analysis of forensic traces. The book comprises the use of Imaging Technologies and will include fingermarks, bodily fluids, gunshot residues, inks and questioned documents.

## Slide 29
Suggest beginning of March 2018 in Brussels